## Backlog
ID | Area | Work Item | Priority | Phase | Owner Role | PRD Ref | Acceptance / Outcome | Status | Target Sprint
BPMS-001 | GOV | Process taxonomy & ownership | P0 | Phase 1 | Backend | G01 | Catalog CRUD, scoped search, RACI | Not Started | TBD
BPMS-002 | GOV | SOP editor and review | P0 | Phase 1 | Fullstack | G03-G05 | Immutable approved versions | Not Started | TBD
BPMS-003 | GOV | Process map + dependency graph | P0 | Phase 1 | Frontend | G02 | As-is/to-be navigation | Not Started | TBD
BPMS-004 | SEC | Tenant identity and authorization | P0 | Phase 1 | Backend | P01 | Cross-tenant negative tests | Not Started | TBD
BPMS-005 | GOV | Review workflow and audit | P0 | Phase 1 | Backend | G04 | Reviewer segregation | Not Started | TBD
BPMS-006 | UX | Business-friendly designer | P0 | Phase 2 | Frontend | E01 | Graph validator and drafts | Not Started | TBD
BPMS-007 | EXEC | Runtime IR and compiler | P0 | Phase 2 | Rust | E01/E07 | Version-pinned compilation | Not Started | TBD
BPMS-008 | EXEC | Durable instance state machine | P0 | Phase 2 | Rust | E06 | Restart/race correctness | Not Started | TBD
BPMS-009 | EXEC | Human approvals and delegation | P0 | Phase 2 | Fullstack | E04/E05 | Concurrent decision safety | Not Started | TBD
BPMS-010 | EXEC | Forms and typed variables | P0 | Phase 2 | Fullstack | E03 | Field validation and privacy | Not Started | TBD
BPMS-011 | EXEC | Timers and escalation | P0 | Phase 2 | Rust | E04 | Crash-safe scheduler | Not Started | TBD
BPMS-012 | INT | Outbox and notifications | P0 | Phase 2 | Backend | E09 | At-least-once dedup | Not Started | TBD
BPMS-013 | INS | Operational metrics | P0 | Phase 2 | Backend | I01 | Accurate SLA dashboards | Not Started | TBD
BPMS-014 | SEC | SSO OIDC/SAML and SCIM | P1 | Phase 3 | Backend | P02 | Deprovisioning test | Not Started | TBD
BPMS-015 | CASE | Case management | P1 | Phase 3 | Fullstack | C01-C02 | Flexible evidence-based cases | Not Started | TBD
BPMS-016 | GOV | Controls and attestations | P1 | Phase 3 | Fullstack | G06 | Evidence exports | Not Started | TBD
BPMS-017 | OPS | Backup restore HA readiness | P1 | Phase 3 | DevOps | P05/P06 | RPO/RTO rehearsal | Not Started | TBD
BPMS-018 | INT | Connector framework | P1 | Phase 3 | Backend | E09 | Secrets and SSRF control | Not Started | TBD
BPMS-019 | UX | Accessibility and onboarding | P1 | Phase 3 | Design | P04 | WCAG audit | Not Started | TBD
BPMS-020 | EXEC | DMN decisions | P2 | Phase 4 | Rust | E10 | Rule table validation | Not Started | TBD
BPMS-021 | INS | Process mining export | P2 | Phase 4 | Data | I03 | Conformant event log | Not Started | TBD
BPMS-022 | AI | AI model drafting | P2 | Phase 4 | Fullstack | Future | Human publish gate | Not Started | TBD

## Roadmap
Phase | Window | Deliverable | Exit Gate
Phase 0 | Weeks 1–4 | Research, spikes, runtime ADR | G1
Phase 1 | Weeks 5–12 | Catalog, SOPs, governance | G2
Phase 2 | Weeks 13–24 | Designer, runtime, approvals | G3
Phase 3 | Weeks 25–36 | Enterprise hardening, cases | G4/G5
Phase 4 | Months 10–18+ | DMN, mining, AI, expansion | Demand gate

## Risks
ID | Risk | Severity | Likelihood | Mitigation | Owner
R1 | Execution correctness | Critical | High | Formal semantics, model tests | Runtime lead
R2 | Full BPMN scope creep | High | High | Subset and compatibility matrix | Product
R3 | Cross-tenant access | Critical | Medium | Tenant safe FK + policy tests | Security
R4 | Low governance adoption | Medium | Medium | Templates, research | Product
R5 | Runtime lock-in | High | Medium | IR, adapter benchmark | Architecture
R6 | Third-party licenses | High | Medium | SBOM and legal review | Engineering
R7 | Version migration | High | High | Pin versions; later migration tool | Runtime
R8 | Duplicate external effects | High | High | Outbox, idempotency | Integrations

## Test Matrix
ID | Test | Category | Pass Condition | Phase | Status
T01 | Duplicate approval | Correctness | Only one transition commits | Phase 2 | Not Started
T02 | Worker killed after commit | Recovery | Outbox eventually delivers | Phase 2 | Not Started
T03 | 30-day wait then resume | Durability | Original version resumes | Phase 2 | Not Started
T04 | Tenant A reads tenant B | Security | Denied and audited | Phase 1 | Not Started
T05 | Expired delegation | Security | Approval denied | Phase 2 | Not Started
T06 | Timer lease expiry | Recovery | Single effective firing | Phase 2 | Not Started
T07 | Published SOP edited | Governance | Published version immutable | Phase 1 | Not Started
T08 | Connector webhook replay | Security | No duplicate effect | Phase 3 | Not Started
T09 | Restore database + objects | Operations | Recovery within RTO | Phase 3 | Not Started
T10 | Keyboard-only publish | Accessibility | End-to-end possible | Phase 3 | Not Started

## Decisions
ID | Decision | Status | Owner | Gate
ADR-001 | Separate governance from execution | Proposed | Architect | G1
ADR-002 | PostgreSQL source of truth | Proposed | Architect | G1
ADR-003 | Versioned process IR | Proposed | Runtime lead | G1
ADR-004 | Friendly modeler + advanced BPMN | Proposed | Product | G1
ADR-005 | Transactional outbox/inbox | Proposed | Runtime lead | G1
ADR-006 | AI requires human approval | Proposed | Security | G1
ADR-007 | Modular monolith initially | Proposed | Architect | G1
ADR-008 | Tenant policy and isolation | Proposed | Security | G1